## Project Tracking
PROJECT PLANNING AND TRACKING | [9 empty] | STATUS KEY | PRIORITY KEY
[10 empty] | On Hold | Low
PROJECT TITLE |  | Design and Development of an Intelligent Operation Center (IOC) for Building Energy Management and Automated Control | [7 empty] | Not Yet Started | Medium
Alexis MARTINI(18/05/2026 - 21/08/2026) |  | Andy CLÉMENT(18/05/2026 - 21/08/2026) | [7 empty] | In Progress | High
Supervisor: Van Lic TRAN | [9 empty] | Complete
PROJECT DETAILS | [7 empty] | DELIVERABLES
STATUS | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE
PHASE 1: IDEATION AND VALIDATING (~2-3 WEEKS) | [8 empty] | 100%
Complete | High | 2018-09-09 | 2018-09-10 | 1 | Task 1 | Alexis | Summary of previous studies and method (Find the related paper on https://dblp.org and on the internet ) Shared doc file |  | 100%
Complete | High | 2018-09-10 | 2018-09-14 | 4 | Task 2 | Andy | Comparison of their advantages and disadvantages to highlight the research gap and propose the method and design |  | 100%
Complete | Medium | 2018-09-11 | 2018-09-20 | 9 | Task 3 | Alexis + Andy | Overall System Design in graph | Update to https://canva.link/cmdibg6ozf8udat | 100%
Complete | Medium | 2018-09-12 | 2018-09-20 | 8 | Task 4 | Alexis + Andy | REPORT: Complete Section: RELATED WORK in the paper | Update to https://www.overleaf.com/6564517495wfhgsshrtfbw#6a6866 | 100%
PHASE 2: PLANINING AND IMPLEMENTING (~5-6 WEEKS) | [8 empty] | 50%
Complete | High | 2018-09-09 | 2018-09-10 | 1 | Task | Gino | API and Data process |  | 100%
In Progress | High | 2018-09-10 | 2018-09-14 | 4 | Task | Gino | Features engineering |  | 80%
Complete | Medium | 2018-09-11 | 2018-09-20 | 9 | Task | Gino | ML pipeline |  | 100%
In Progress | High |  |  |  |  | Gino | Finding the best parameters ML/features |  | 20%
Not Yet Started | Low | [5 empty] | Ready to use location predictor program |  | 0%
Not Yet Started | Medium | 2018-09-12 | 2018-09-20 | 8 | Task |  | REPORT: Complete Methodology / Proposed Method and Experimental Setup / Simulation in the paper | Update to https://www.overleaf.com/6564517495wfhgsshrtfbw#6a6866 | 0%
PHASE 3: RESULTS AND EVALUATION (~3-4 WEEKS) | [8 empty] | 0%
On Hold | High | 2018-09-09 | 2018-09-10 | 1 | Task |  | Experimental/simulation scenarios |  | 0
Not Yet Started | Low | 2018-09-10 | 2018-09-14 | 4 | Task |  | Evaluation metrics |  | 0%
In Progress | Medium | 2018-09-11 | 2018-09-20 | 9 | Task |  | Comparison with existing methods |  | 0%
Complete | Medium | 2018-09-12 | 2018-09-20 | 8 | Task |  | REPORT: Complete Section: Results and discussion and Conclusion in the paper. Finalize the paper, prepare to submit | Update to https://www.overleaf.com/6564517495wfhgsshrtfbw#6a6866 | 0%
PHASE 4: TRANSITION (~ 1 - 2 WEEKS) | [8 empty] | 0%
On Hold | High | 2018-09-09 | 2018-09-10 | 1 | Task 1 |  | Packaging project |  | 0
Not Yet Started | Low | 2018-09-10 | 2018-09-14 | 4 | Task 2 |  | Storing (source code) and write instruction, need to check the reproducibility |  | 0%
In Progress | Medium | 2018-09-11 | 2018-09-20 | 9 | Task 3 |  | Slide for the Final presenation |  | 0%
Complete | Medium | 2018-09-12 | 2018-09-20 | 8 | Task 4 |  | Details of task here |  | 0%

## Project Description
Project definition
Project Goals:
- Users can monitor the health status (e.g., cardiovascular activity, falls, stroke, heart attack,…) and behavior (e.g., emotions,…) of elderly individuals via a mobile phone, with a test accuracy of over 90%.
-The system can operate and be tested with users in real-world conditions.
Publication
- Submit 01 paper IEEE Journal of Biomedical and Health Informatics.